## Sheet1
Test Report Project Name: HR Tool Interne Positionsvermittlung
Test Cycle-2 | Functional Testing,Unit Testing, Regression Testing
EXECUTED | PASSED | 15
| FAILED | 5
| (Total) TESTS EXECUTED (PASSED + FAILED) |  | 20
PENDING |  |  | 10
IN PROGRESS |  |  | 5
BLOCKED |  |  | 0
(Sub-Total) TEST PLANNED |  |  | 35
(PENDING + IN PROGRESS + BLOCKED + TEST EXECUTED)
DEFERRED |  |  | 0
Feature/Components | # Tests Planned | % Tests Executed | % Tests Passed | # Deferred(Inprogress,pending)/ blocked | Status(<Green/ Red/ Yellow>) | Remarks
Login Page | 5 | 80% | 75% | 1 |  | Few UI Issues to be fixed
Job Seeker Functionalities | 6 | 100% | 100% | 0
Admin Functionalities | 5 | 60% | 100% | 2 |  | Few Pending and Inprogress
Recruiter Functionalities | 11 | 27% | 33.33% | 8 |  | Few Pending and Inprogress
Forgot Password | 4 | 75% | 33% | 1 |  | Few inprogress
UI Features | 8 | 62.5% | 20% | 1 |  | UI Issues
Defect | Description | Test Case ID | Originator Page | Severity | Opendate | Status<open/Clsoe>
"Unknown user or password." Error message not being displayed | 1. Go to the launch / login page of the application 2. Enter invalid email and password in the mentioned fields 3. Click on Login | TC2 | Login Page | Low | 14/7/2017 | Open
Invalid email id (Ex: abc) and invalid category (Ex: ag)is accepted during registration | 1. Go to the launch / login page of the application 2. CLick on Hire People button and go to Recruiter Registration page 3.Enter Invalid Email ID and invalid category in Email and category field | TC24 | Recruiter Registration Page | High | 14/7/2017 | Open
Less than 6 and more than 6 digits also accepted including alphabets are also accepted | 1. Go to the launch / login page of the application 2. Click on Hire People button and go to Recruiter Registration page 3.Enter Employee IDs less than 6 digit and more than 6 digit in the Employee ID field 4.Also Enter Alphabets in Employee ID | TC25 | Recruiter Registration Page | High | 14/7/2017 | Open
Valid but unverfied user is allowed to reset password | 1) Go to the Forgot password page 2) Enter valid but unverified ID to reset password ex: Instructions on how to reset your password have been sent to abc2z@gmail.com. Ex: An unverfied email ID abc2z@gmail.com was given in reset password field and above message was displayed | TC30 | Forgot Password Page | High | 14/7/2017 | Open
Invalid Email ID could be used to reset password | 1) Go to the Forgot password page 2) Enter invalid ID to reset password ex: Instructions on how to reset your password have been sent to abc2z@gmail.com. Ex: An unverfied email ID abc2z@gmail.com was given in reset password field and above message was displayed | TC31 | Forgot Password Page | High | 14/7/2017 | Open